### BPG BEST PRACTICE GUIDELINE

| BPG-2 | Date of Implementation |
| --- | --- |
| RISK MANAGEMENT |  |
|  | Date Reviewed |
| APPLICATION | Date Due for Review |

# MANAGING RISK

Managing risk is an integral part of good management.  The application of a risk management process will improve procurement outcomes.   It will provide opportunities to reduce costs, and to improve economic, social, environmental and technological outcomes.

Risk Management does this through:

- Identifying and reducing exposure to risk.

- Providing greater certainty and insight to support decision making;  and

- Improving contingency planning for dealing with risks and their impacts.

# WHAT IS RISK?

Risk is the possibility that an expected outcome will not occur, or that an unforeseen event will occur.  Risk can arise from either:

- Limited information, experience and knowledge on which to base decisions;  or

- Uncertainty of future events.

Risk is usually measured in terms of:

- Consequences – what will happen.

- Likelihood – the chances of it happening.

In procurement, risk may come from:

- Factors under the control of an agency and its procurement personnel (e.g., ethics and probity, experience, expertise, competency, financial and technical skills, knowledge of the applicable procurement and contract system, identification of product and/or service requirements).

- Factors under the control of the Service Provider (e.g., ethics and probity, experience, expertise, competence, materials, financial and technical skills, contract planning and management, innovation, production processes, delivery, installation, service and maintenance).

- Factors involved in the contractual relationship (e.g. contract planning, service delivery, communication, contract management and liability for damages).

- Factors outside the control of the parties (e.g., industrial disputes, changes in interest and exchange rates).

- The goods and services procured (e.g., documentation, serviceability, timeliness, reliability, technology issues and quality).

# WHAT IS RISK MANAGEMENT?

Risk Management identifies potential risks, analyses their consequences, and devises and implements responses to ensure that procurement and service delivery goals are achieved.  The aim is to achieve more reliable planning, improved decision making and greater certainty of outcomes.

By managing risk, agencies can identify potential problem areas that may adversely affect the desired procurement outcomes, improve the understanding of risk profiles of different procurement, and understand how future decisions may affect that profile.  It reduces the uncertainty of outcomes and economic loss.  Risk management is as much about identifying opportunities to improve the delivery of goods or services as it is about avoiding or mitigating losses.

Risk management activities should always add value to the procurement process.  The effort expended in managing risk should be commensurate with:

- The nature of the procurement.

- The cost of the procurement.

- The complexity of the procurement;  and

- The significance of the procurement to the agency.

The risk management process is applicable to all stages of procurement, from identifying a need, satisfying that need, and ultimately through to disposal.  It is an integral part of good procurement management.  Effectively managing risk can lead to significant savings in resources, timely delivery and improved quality of services and relationships with clients.

# USING RISK MANAGEMENT

‘Procurement’ is defined as the process involving all activities following the decision that a good or service is required and involves the acquisition and disposal of goods and services.  Risk management is essential in all stages of the procurement process, from the initial planning stages and throughout the life of the procurement.

Risk management involves proactive consideration of each procurement and its associated risk.  This also includes factors occurring prior to the decision to procure, for example, decisions concerning service contracting.  The use of service contracting does not abrogate agencies’ legal and other managerial responsibilities.

Procurement personnel should assess the risk involved in procurement activities by evaluating the product or service, its relative value and how critical it is to the agency.

Managing risk in procurement can be achieved by using a checklist, through to the development of a risk management plan.  Attachment 1 is a checklist covering some of the potential risks in the procurement process.

| High | Moderate risk – specialised goods and services – high technology goods – specialist knowledge services – difficult or limited supply – complex specifications – moderate potential for accidents or injury | Major risk – high technology goods – specialist knowledge services – long term procurements – small or uncompetitive market – very complex specifications – major potential for accident or injury |
| --- | --- | --- |
| Impact | Low risk – small orders of basic goods and services – common use items – established competitive market – low potential for accidents or injury | Moderate risk – widely or often used goods and services – low technology – many suppliers – simple specifications – minor potential for accident or injury |
| Low | Value | High |

Risk Reduction Matrix

# WHAT IS A RISK MANAGEMENT PLAN?

A risk management plan is a document outlining the potential risks for a complex procurement program, project or activity.  It records the identified risks, the likely consequences of these risks, and the options to treat and monitor them.

A risk management plan should be undertaken when:

- The value of the purchase is high.

- The procurement process is complex.

- Adverse consequences could significantly affect the agency’s operation.

- Delivering core business services to the community is significantly affected.

- There are other mitigating factors, for example, industrial relations, workforce development, environmental and OHS&R.

Plans will vary from one agency to another, depending on the needs of the particular agency, its goals, the services it intends to provide, and the specific strategies adopted.

Attachment 2 is a sample format for a risk management plan for a complex procurement program, project or activity.

# ONGOING RISK MANAGEMENT MONITORING

As risks may change during the course of a procurement program, it is periodically necessary to review the effectiveness of the initial risk provisions and management course adopted and update them as circumstances and risk exposure change.

For complex procurement, several risk assessments may be needed. These may be at various stages, such as:

- Concept development.

- Acquisition.

- Operation and maintenance;  and

- Disposal.

# THE RISK MANAGEMENT PROCESS

The process outlined in this guideline serves as a guide and can be adapted on a case by case basis.

While the process is essentially sequential, in practice, it is often necessary to revisit previous stages as the process proceeds and to reconsider earlier decisions when new information becomes available.

Risk management involves 7 stages:

- Establishing the risk context
What is the issue to be considered or decision to be made?  
What are the circumstances of the issue?

- Identifying potential risks
What, why and how might things affect the issue or decision?

- Analysing the risk
How likely is each risk?
What could be the consequences?
What is the overall magnitude of the risk?

- Assessing and prioritising the risk
Which risks are acceptable?
Which risks should be avoided?
Which risks require treatment?

- Treating the risk

- Preparing and implementing treatment plans

- Monitoring and reviewing

STAGE 1 – ESTABLISHING THE RISK CONTEXT

This is the preparatory stage.  It results in familiarity with the proposed procurement and identifies key parameters and assumptions.

# DEFINE THE OBJECTIVES

This involves defining the nature and scope of the procurement, its key objectives and outcomes.

# DEFINE THE PREVAILING CIRCUMSTANCES

Consider those factors which may influence performance of the procurement activity, and the risks to which it will be exposed, in particular:

- Relevant service delivery goals and strategies.  Identify relevant goals and the strategies in place to achieve them.  If the procurement relates to the agency’s procurement plan, define the outcomes.

- External factors that may affect the procurement.  External factors often have a major impact on the procurement of goods and services and therefore need to be identified.  These may include social, technical, economic, environmental and OHS&R factors.

- The expectations of stakeholders such as users, local communities, government agencies and Service Providers.  Where appropriate, consult stakeholders to clarify their expectations and their attitude to risk.

Understanding these issues helps define the criteria by which it is decided whether a risk is acceptable or whether risk treatment options need to be considered.

# DEVELOP RISK CRITERIA

Define the criteria against which to judge identified risks.  In the planning stages of the procurement, the criteria will reflect strategic concerns.  In the procurement, maintenance and disposal stages, the criteria are likely to concern efficient completion, cost control, quality, compliance and so on.

Examples of risk criteria are:

- Achievement of procurement outcomes.

- Delivering on time and budget.

- Maintaining high probity standards.

- Achieving high levels of competition.

Future decisions on whether risks are acceptable or not should be based on these types of criteria.

# BREAK DOWN THE PROCUREMENT ACTIVITY INTO KEY ELEMENTS

When identifying risk, it is often helpful to break the activity down into key elements or stages.  For example, procurement can generally be broken down into planning, documentation, tendering, and contract management stages.  The stages will vary for each type of procurement, depending on the type and complexity of the activity and the nature of the risk.

Attachment 1 provides an example of the procurement cycle broken down into key stages, with possible risks associated with each.

# STAGE 2 – IDENTIFYING POTENTIAL RISK

This stage identifies the risks that might affect each key element of the procurement process.  The aim is to generate a comprehensive list of the possible risks, and document what each one involves.

Consider all risks, whether or not they are under the control of the agency.  Ask 2 questions:

- What can happen?  Compile a list of the possible events that could have an unwanted or unintended effect on the procurement.  Consider the full life cycle of the good or service and include problems that may arise after the goods are received or the service performed.

- How and why could it happen?  Explore the events identified in the first question for their possible causes and implications.

There are several ways to identify risks and their causes.  It is helpful to break the activity down into key elements or stages and identify the risk for each element.  Checklists also provide a useful starting point.

Agencies carrying out many similar procurements may find it useful to develop checklists based on past experience.  Examine the records of similar procurements.  From these, you can develop:

- Flow charts of the sequentially connected set of events with outcomes.  A flow chart helps to clarify and understand the steps in the process by documenting in proper sequence the flow of events.

- Scenario analysis.  This a tool for identifying what might happen in the future and developing responses.

When the list of risks is assembled, a preliminary analysis should be carried out to cull any low impact risks from further consideration.

# SOURCES OF INFORMATION

Use all the available data sources to understand the risk.  These may include:

- Relevant experience.

- Industry practice.

- Pilot schemes and prototypes.

- Past performance.

- Financial models.

- Specialist advice.

# STAGE 3 – ANALYSING THE RISK

The next stage is to estimate the likelihood of a risk arising and its potential consequences.

Determine the overall risk level by combining estimates of likelihood, and consequence in the light of existing controls.  These are the management and other systems that are already in place to control risk.  For example, where community involvement in procurement is concerned, many use consultation mechanisms to promote community awareness and manage possible concerns.

The analysis of likelihood and consequence may be undertaken to varying degrees of refinement, depending on the scale of potential risk and the data available.  The greater the potential risk, the greater the level of analysis required.  The key questions are:

- How likely is the event?

- What are the consequences of the event?

- What is the overall risk level?

# HOW LIKELY IS THE EVENT?

The likelihood of an event can be described:

- In qualitative terms.  Qualitative methods use words to describe the likelihood (e.g., low, medium, high).

- In semi-quantitative terms.  These use numbers subjectively matched to qualitative scales to describe the likelihood.  The number assigned need not have an accurate relationship to the magnitude of the likelihood.  Rather, the objective is to produce a more analytical prioritisation of risk than is achieved through qualitative methods (e.g., rare = 0.1, unlikely = 0.3, moderate = 0.5, likely = 0.7, almost certain = 0.9).

- In quantitative terms, for example in terms of probability or frequency.

Qualitative and semi-quantitative methods are relatively simple to apply, and do not require extensive time and resources.  They are useful when resources are limited or when data is not available for more rigorous analysis.  Quantitative methods on the other hand require time, resources and extensive data.  They are used most often to analyse financial and technical risk.

# WHAT ARE THE CONSEQUENCES OF THE EVENT?

As with likelihood, consequences can be described:

- In qualitative terms.

- In semi quantitative terms;  or

- In quantitative terms.

Consequences should be expressed in terms of the risk criteria identified in Stage 1 – Establishing the risk context.

# WHAT IS THE OVERALL RISK LEVEL?

Finally, combine the likelihood and consequences of the risk to produce a level of risk.  An overall risk factor will be high if the risk is likely to occur or its impact is large, and highest if both are present.  A simple way to illustrate levels of risk for various events is to create a matrix, as illustrated below.

|  |  | ##### Consequence |  |  |
| --- | --- | --- | --- | --- |
|  |  | ##### Low | Medium | High |
| #### Likelihood | Low | Event 1 |  | Event 2 |
|  | Medium |  | Event 3 |  |
|  | High | Event 4 |  | Event 5 |

# STAGE 4 – ASSESSING AND PRIORITISING THE RISK

This step involves the priortising of risks for further action.  In most cases, there are 3 categories of risk:  low, moderate and high.

# CATEGORIES OF RISK

Low risks (designated P1 on next page) are usually involved with purchases of readily available and commonly used goods or services (e.g., office supplies).  These risks can be accepted and managed by routine procedures.

Moderate risks (P2) usually come from purchases of commonly used goods or services, which involve a complex element such as technology or specialist knowledge.  These risks should be monitored and managed by routine processes, as long as the situation is constant.  They should be moved up to the high risk category if the likelihood or potential consequences increase.

High risks (P3) occur in procurements which involve high costs, long term supply, innovative technology or services, or provide an essential good/service to the agency.  These risks require a specific treatment plan.

Using the matrix demonstrated previously, a typical allocation of priorities and responses could be:

|  |  | ##### Consequence |  |  |
| --- | --- | --- | --- | --- |
|  |  | ##### Low | Medium | High |
| #### Likelihood | Low | P1 |  | P2 |
|  | Medium |  | P2 |  |
|  | High | P2 |  | P3 |

Alternatively, using a semi quantitative approach, an example of priorities can be determined as illustrated:

| ##### Event | Likelihood | Consequence | ##### Level | ##### Priority |
| --- | --- | --- | --- | --- |
| 1 | 0.2 x | 0.3 = | 0.06 | P1 |
| 2 | 0.3 x | 0.9 = | 0.27 | P2 |
| 3 | 0.5 x | 0.5 = | 0.25 | P2 |
| 4 | 0.7 x | 0.3 = | 0.21 | P2 |
| 5 | 0.8 x | 0.7 = | 0.56 | P3 |

Explanatory note to table:  ‘Likelihood’ is the risk likelihood measured on

a scale 0 to 1;  ‘Consequence’ is the impact measured on a scale 0 to 1.

The assessment will vary from situation to situation, depending on individual circumstances.

The output of Stage 4 is a prioritised list of:

- Risks to be treated.

- Risks to be accepted and monitored;  and

- Acceptable risks for the procurement.

# STAGE 5 – TREATING THE RISK

Risk treatment must be appropriate to the significance of the risk and the importance of the activity.

For high priority risks requiring treatment, this stage involves:

- Identifying potential treatment options.

- Evaluating and selecting appropriate options;  and

- Preparing and implementing risk treatment plans.

Risk treatment options may include:

###### Avoid the risk

Avoid the risk by:

- Deciding not to proceed with the activity that causes the risk;  or

- Seeking alternative means of achieving the outcome.

###### Transfer the risk

Transfer risk by shifting responsibility from the agency to another party, which ultimately bears the consequences if the risk arises.  Agencies will normally incur a cost for the other party assuming the risk.

Insurance is a common risk transfer strategy.  Contracts and specific terms of a contract between an agency and its Service Providers are the primary means of allocating risk between the parties involved in procurement.

The general principle when considering whether to transfer a risk is that responsibility for the risk should be borne by the party best able to control and bear that risk.

###### Accept the risk

Accept risk when it cannot be avoided or transferred, or the cost of doing so would not be worthwhile.  It is recommended that risk reduction or impact mitigation measures and monitoring be employed in these circumstances, as appropriate.

###### Reduce the likelihood of occurrence

Where the risk has to be accepted, minimise the likelihood of the risk occurring.  Reduce the likelihood of risk by:

- Clarifying the requirements, specifications and outcomes.

- Revising procedures.

- Specifying quality assurance (Attachment 3 provides further information on the application of quality assurance in risk management).

- Specifying product standards.

- Conducting product testing and inspection.

- Specifying professional accreditation.

- Including warrantees and guarantees;  and

- Managing the relationship between customers and Service Providers.

###### Reduce the consequences

Measures to reduce the impact of risks include:

- Contingency planning.

- Contract terms and conditions.

- Inspections and checks to detect compliance;  and

- Recovery programs.

# EVALUATE AND SELECT THE APPROPRIATE OPTIONS

Selecting the most appropriate option involves balancing the cost of implementing each option against the benefits derived from it.  In general, the cost of managing risks should be commensurate with the benefits obtained.

In many cases, a combination of options will give the best overall result.  For example, it may be best to take steps to reduce the likelihood of risks, reduce their consequences, and then accept any residual risks.

# STAGE 6 – PREPARING AND IMPLEMENTING TREATMENT PLANS

Prepare treatment measures for moderate risks.  Treatment measures are simple action statements that specify the activities necessary to meet the risk events.

For high risks, draft a risk treatment plan to document how the risk will be managed.  Typically the plan should show:

- Actions and expected outcomes.

- Timetables.

- Resource budgets (personnel, costs and data).

- Responsibilities.

- Reporting requirements;  and

- Monitoring requirements.

The most important task in risk management is implementation of the treatment plan.  Planning for implementation requires particular attention to the resources required, management responsibilities and the timing of tasks.

Record the risk treatment plan and implementation strategies in the risk management plan.

Is risk acceptable?

Yes

Accept the risk

No

Reduce likelihood

Reduce consequences

Transfer in part or full

Avoid

# Evaluate options and select strategies

# Prepare treatment plan, implement and review regularly

# STAGE 7 – MONITORING AND REVIEWING

Few risks remain static.  Consequently, it is necessary to monitor the risk treatment plan and the effectiveness of its implementation.

It is not sufficient to simply prepare a risk management plan at the initial procurement decision.  It must be regularly reviewed to ensure its ongoing relevance, and amended if circumstances change.

If the procurement is of high value, strategic or complex, the risk management plan should specify and detail the review process.

ATTACHMENT 1

CHECKLIST OF POTENTIAL RISKS IN THE PROCUREMENT PROCESS

| ##### Risk | Likely Consequences | Action |
| --- | --- | --- |
| Understatement of the need | Purchase of unsuitable product or services Money wasted Need not satisfied Additional cost | Analyse need accurately Ensure industrial relations, environmental, OHS&R, economic and workforce outcomes are considered |
| # Overstatement of the need | Greater expense Poor competition | Analyse need accurately, include functional and performance requirements |
| Insufficient funding | Delay in making the purchase Additional costs for re-tender | Obtain appropriate approvals before undertaking process Improve planning |
| Impractical timeframe | Inadequate service provider responses Reduced competition Delivery schedule not met | Improve forecasting, planning and consultation with users Improve communication with potential service providers |
| Probity issues | Increased procurement costs Misuse of resources Most suitable product not obtained Unethical conduct | Improve forecasting, planning and consultation with users Improve communication with potential service providers |
| Misinterpretation of user needs | Totally unacceptable purchase or not most suitable product or service Time lost Increased costs Possible downtime | Improve consultation with users Obtain clear statement of work and definition of need |

# DEVELOPING THE SPECIFICATION

| ##### Risk | Likely Consequences | Action |
| --- | --- | --- |
| Narrow definition or commercial specification (e.g., brand name) | Fewer alternatives Most suitable product or service may not be obtained Increased costs | Define the required outcomes Develop functional or performance specifications |
| # Definition of inappropriate product or service | Need not satisfied Time lost Increased costs Possible downtime | Ensure specification is consistent with needs analysis Market knowledge Functional or performance specifications |
| Biased specification | Inadequate service provider response Claims of unfair dealings | Use common use contracts Use functional or performance specifications Control mechanism to review specification before release |
| Inadequate specification or statement of work (for services) | Variety of offers Insufficient responses Products offered not meeting needs Difficult to evaluate | Be familiar with requirements Use functional or performance specifications Use expressions of interest or requests for information |

SELECTING THE PROCUREMENT METHOD

| ##### Risk | Likely Consequences | Action |
| --- | --- | --- |
| Failure to identify potential sources | Lack of offers from suitable service providers | Improve procurement planning and system selection Improve market knowledge Seek industry participation Use Industrial Supplies Office Develop industry impact statements Require service providers to provide a local industry participation plan |
| Selecting inappropriate method | Need to seek offers again Possible cost variations Failure to obtain value for money Excessive number of inappropriate bids High cost to bidders High cost of evaluating tenders | Ensure IR, ESD, OHS&R and workforce outcomes are considered Improve implementation of Codes of Practice and tendering, procurement policies, guidelines and practices Improve knowledge and expertise in tendering methods Provide staff with appropriate training and experience |

# CONTRACT DOCUMENTS

| ##### Risk | Likely Consequences | Action |
| --- | --- | --- |
| Terms and conditions unacceptable to service providers | Loading of costs in offers Having to modify tender terms and conditions Disruption Low response | Improve tender planning and procurement system selection Assess and allocate risks appropriately Gain commercial expertise Use commercially acceptable terms Assess conditions of contract and select appropriate conditions Provide staff with appropriate tender planning and procurement skills |
| Providing inadequate information | Loading of costs in offers Variations in offers Having to provide clarifying information, causing delays in tender closing Additional costs | Ensure staff have appropriate tender planning and documentation training and experience Improve tender planning and preparation Review tender documents before issuing them and ensure selection criteria contain the critical factors on which assessment of tenders will be based |

SEEKING, CLARIFYING AND CLOSING OFFERS

| ##### Risk | Likely Consequences | Action |
| --- | --- | --- |
| Failure to address service provider enquiries adequately | Claims of unfair practices Offers with qualifications by tenderers Withdrawal of offers | Implement standardised procedures for responding to enquiries Provide staff with appropriate tender management training and experience Respond in a timely manner to service provider enquiries Allow adequate time for tenderers to respond |
| Actual or perceived favouritism in providing information | Service provider complaints Withdrawal of offers | As above actions and Provide all service providers with any addendum that may be required |
| Actual or perceived breach of confidentiality | Service provider complaints Mistrust by service providers | Establish formal security procedures Train staff in their obligations Perform regular audits and reviews of security processes Advise service providers of measures |
| Insufficient number of responses | Need to undertake process again Increased costs Delayed delivery to the client Poor value for money due to limited competition | Use appropriate tender advertisement strategy to increase competition Provide service providers with advance notice of tender requests Improve tender documentation and specifications Allow sufficient time for tenderers to respond |
| No response from known quality service providers | Reduced competition Increased costs of products or services | As above actions for insufficient number of responses Improve your market knowledge Review specifications or conditions Seek feedback from known service providers on their non response |

EVALUATING OFFERS

| ##### Risk | Likely Consequences | Action |
| --- | --- | --- |
| Failure to follow effective evaluation procedures | Selection of wrong offer Inconsistent evaluations Possible service provider complaints Subjective not objective evaluation of offer | Provide staff with appropriate tender assessment and evaluation training and experience Improve tender assessment and evaluation processes Maintain, audit and review evaluation procedures |
| Breaches of security | Claims of unethical or unfair practices Loss of faith with service providers | Maintain, audit and review security procedures Review and improve the agency’s Code of Conduct as appropriate Provide staff with appropriate training and experience and monitor performance |
| Offers fail to meet needs | Need to call tenders again Additional costs Delay in delivery | Improve market knowledge Improve tender documentation Conduct market research Develop functional or performance specifications |
| Failure to identify a clear winner Decision made on subjective grounds | Claims of unethical and unfair behaviour Service provider complaints | Ensure selection criteria contain the critical factors on which assessment of tenders will be based and are clearly identifiable to tenders in tender documents |

SELECTING THE PREFERRED SERVICE PROVIDER

| ##### Risk | Likely Consequences | Action |
| --- | --- | --- |
| Selecting an inappropriate service provider | Failure to fulfil the contract | Provide staff with appropriate tender evaluation, financial and technical skills training and commercial expertise Improve evaluation procedures Improve selection criteria and clearly identify to tenderers in tender documents Reject unacceptable offers Perform financial, technical and company evaluations before awarding contract |
| Selecting inappropriate product | Failure to meet the client’s need | Ensure users are involved in the selection process/evaluation Improve technical evaluation procedures and train staff as appropriate |

NEGOTIATIONS

| ##### Risk | Likely Consequences | Action |
| --- | --- | --- |
| Not matching the expectations of buyer and service provider | Contract dispute Delivery delays Cost variations Reduction in value for money Purchase of less suitable product Inefficient use of resources | Improve communication Provide staff with training in contract planning and management Define terms carefully Record each party’s obligations Clarify all ambiguities before signing the contracts |
| Deadlock on details of agreement | Delays in delivery Need to restart procurement Possible cost of legal action | Look at alternatives to share risk Distinguish between essential and non essential goals and requirements |
| Failure to secure mandatory conditions | Inability to finalise contract Delays in delivery Variations in cost Inefficient use of resources | Establish baseline before negotiations Distinguish essential goals from others Consider variations to contract Provide negotiators with adequate training |
| Unfair or onerous requirements on the service provider in the contract conditions | Contract disputes Invalidity of contract Legal action Poor service provider/customer relationship | Provide negotiators with adequate training and support Negotiate commercial terms Terms should be fair and reasonable |
| Failure to reflect the terms offered and agreed in the contract | Contract disputes Legal action Poor service provider/customer relationship | Check final draft of contract with service provider Keep records of all negotiations and agreements |
| Inadvertently creating a contract without the delegate’s prior approval | Expense of negotiating out the contract and paying damages Committing to other associated work prior to main contract existing | Procedure in place to ensure delegate’s approval obtained first Provide negotiators with adequate training |

CONTRACT MANAGEMENT

| ##### Risk | Likely Consequences | Action |
| --- | --- | --- |
| Variations in price and foreign exchange | Cost overruns | Agree on prices and the basis of prices Agree on a formula for calculating variations Consider a Bill of Exchange or other appropriate means to reduce the risk of exchange rate fluctuations |
| Unwillingness of the service provider to accept the contract | Delays in delivery Need to restart procurement | Seek legal redress if non acceptance causes loss Negotiate but retain integrity of the contract |
| Failure of either party to fulfil the conditions of the contract | Contract disputes Failure to satisfy needs Delays in delivery Downtime Legal action | Ensure good contract administration and performance management Hold regular inspections and ensure progress reports Ensure all staff know responsibilities and conditions Ensure good record keeping and documentation |
| Inadequately administering the contract | Cost increases Failure of contract Full benefits not achieved Delivery of unsatisfactory product Contract/supply disputes | Maintain up to date agency procedures and practices Ensure all staff are suitably trained and experienced in contract planning and management |
| Commencement of work by the service provider before contract is exchanged or letter of acceptance issued | Potential liability to pay for unauthorised work Possibility of legal action for perceived breach of contract | Confirm verbal acceptance of contract with written advice Accept all contracts in writing Ensure approvals are received before allowing work to start |
| Unauthorised increase in scope of work | Unanticipated cost increases Contract disputes | Ensure all contract amendments are issued in writing Record all discussions and negotiations Confirm instructions in writing |
| Loss of intellectual property | Loss of commercial opportunity Unwarranted reliance on service provider for product support | Ensure suitable clauses are included in the contract |
| Failure to meet liabilities of third parties (e.g,. royalties or third party property insurance) | Legal action Damage to the agency’s professional reputation | Check that all obligations are covered in the contract Agree on responsibilities Implement appropriate safety standards and programs |
| Loss or damage to goods in transit | Delays in delivery Downtime Liability disputes | Include appropriate packaging instructions in specification Agree on insurance cover for service provider to provide Accept delivery only after inspection Know when title of goods is transferred to buyer |
| Fraud | Misuse of resources Legal action Disruption to procurement activities | Maintain an ethical environment Follow and maintain fraud control procedures |
| Key personnel not available | Progress on project disrupted Less expertise | Include requirement in expression of interest, request for information, request for tender and ensure compliance in post tender negotiation Know the market Accept risk and manage possible delay |

DISPOSAL

| ##### Risk | Likely Consequences | Action |
| --- | --- | --- |
| Collusive bidding at auction | Not achieving best return Claims of unethical and unfair practices | Set reserve prices Deal with reputable firms Include disposal clause in initial contract Maintain ethical environment |
| Inadequate tender management | Claims of bias and favouritism to organisations and individuals Reduction in value for money | Sell by open tender Document reasons for decision Provide staff with appropriate training |

EVALUATING THE PROCUREMENT PROCESS

| ##### Risk | Likely Consequences | Action |
| --- | --- | --- |
| Failure to evaluate procurement and management processes | Failure to improve procurement and management processes | Develop systematic evaluation methods, techniques and evaluation criteria |
| Failure to identify and address problems | Procurement objectives not achieved Possible failure in the future | Agree on performance criteria (with service provider and customer) Develop good relationships with service providers Include evaluation clause in the contract Implement performance management strategies |

ATTACHMENT 2

TYPICAL FORMAT OF A RISK MANAGEMENT PLAN

- Procurement context

  - Description of the procurement

  - Identify the procurement environment and stakeholders

  - Identify the risk criteria of the procurement

  - Plan the key stages of the procurement

- Risk identification

  - Identify and schedule potential risks and their impacts

- Risk analysis

  - Assess risk likelihood and consequences

  - Determine risk levels

- Risk assessment

  - Undertake risk priority ranking

  - Determine risks to be accepted and monitored

  - Identify risks to be treated

- Risk treatment

  - Evaluate and select risk treatment options

  - Prepare risk treatment plans and implementation strategies

- Ongoing monitoring

6.1  Develop schedule for ongoing review

ATTACHMENT 3

QUALITY ASSURANCE IN PROCUREMENT

Quality assurance is a risk treatment tool that can be used to reduce the likelihood of risks occurring and the consequence of some risks, and help deliver goods and services that are more consistent, reliable, conforming and better supported by the service provider.

Agencies decide on the quality assurance requirement for each procurement on a case by case basis, considering:

- The level and consequence of the risks involved.

- The value of the purchase;  and

- Whether requiring quality assurance will add value to the purchase.

Agencies must ensure that quality assurance does not substantially reduce competition and that it adds value to the procurement of the goods and services.

Use quality assurance to:

- Reduce the perception of risk (by providing confidence that service providers can consistently meet requirements).

- Reduce the possible costs and consequences of risks (particularly in contract administration/management).

- Obtain value for money for the agency.

As agencies establish more strategic supply arrangements, risk assessment and quality assurance become more critical.  Operating quality programs helps to ensure service providers have systems in place that will provide goods and services to specifications.

WHAT LEVEL OF QUALITY ASSURANCE?

A recommended approach is to use the risk reduction matrix and consider the risk and value of a procurement.  The means for assuring quality can cover the spectrum from international standard AS/NZS ISO9000 quality systems to guarantees and past performance.  An agency must be confident that the goods and/or services it has procured will meet the specifications.  Having assessed the risks associated with the procurement, the agency can determine what method of quality assurance would best address the risks identified.  See below.

| High | High risk/Low value Select or negotiate an appropriate solution that may include ISO 9000, product testing, or a pilot program | High risk/High value ISO 9000 and others may be required, as well as project testing |
| --- | --- | --- |
| Risk | Moderate risk and value Some management systems or product testing may be suitable |  |
|  | Low risk/Low value Normal commercial practices may be suitable | Low risk/High value A Quality Assurance system or product testing system may be necessary |

Low							Value				    High

RELATED POLICIES

Policy No	Policy Name

AUTHORISATION	................................................	...................................

(Date)

EXECUTIVE DIRECTOR